## Slide 1: Controlling Rheology via Boundary Conditions in Dense Granular Flows; Karen Daniels, et al.
Updates:
Cambridge: Nathalie is no longer funded, so her work was not include in my report. But conversations, if not direct collaboration, are ongoing
If the video did not seem "new" it was because she talked about the results existing in preliminary forms last year, while continuing to work on them to solidify and quantify them. Since there were only 2 months from the December report when the group left the lab, she did not get a chance to complete the work we had intended to complete this spring

## Slide 2: Controlling Rheology via Boundary Conditions in Dense Granular Flows; Karen Daniels, et al.
Question: I cannot recall why her apparatus cannot rotate faster
Answer: The motor + gearbox cannot drive our flow any faster than we have shown. This is why we involved Nathalie Vriend in the collaboration, and successfully took faster data in her apparatus. Our planned Year 3 (to start this fall) was scheduled to be the construction of a hopper flow that allows for intermediate flows here at home. Some of the work this past year has been development-work on the imaging system that will allow us to collect higher-speed data. This will need a different lighting and camera setup than existed in the previous apparatus. I have solved the expense of a high-speed camera by borrowing it from another project in the group. So, faster speeds are coming but require us to be back in the lab in order to achieve.

## Slide 3: Controlling Rheology via Boundary Conditions in Dense Granular Flows; Karen Daniels, et al.
Question: what are the limits of the stiffness of the outer wall of Karen's apparatus? Can it be released in order to provide a free (or almost free) surface?
Answer: Stiffness: it is adjustable-stiffness in principle (but we've only made real experiments with 1 stiffness), but then for the roughness experiments we had to move away from using that boundary, since it doesn't allow for roughness to be controlled independent of stiffness. No: it cannot be "released" as it is composed of leaf-springs, each of fixed stiffness.

## Slide 4: Controlling Rheology via Boundary Conditions in Dense Granular Flows; Karen Daniels, et al.
Question: I would appreciate some discussion about the impact of the missing data, and what might be done to fill in those gaps.
Answer: There is a lower limit to *any* force technique, and the use of photoelasticity for force measurements will not do worse than the spring boundaries. The real reason for using it its that it has the significant benefit (once we get everything calibrated) of measuring the full stress tensor as a function of radial position, rather than us just a fit of two endpoints a presumed stress function, as was done in Zhu Tang's work. This fills in a gaping hole in the spatial data (we don't have a serious gap in force resolution that causes us particular problems).
Answer: Using this technique the same types of measurements we did with Nathalie Vriend become possible: that work was based on her fast camera + apparatus, and our photoelastic analysis code. Once we go to to more collisional flows, the low-force resolution could become a problem, as it was near the surface of Nathalie Vriend's flows, but we don't expect this a problem for us since we won't be studying a free surface flow as she was. This is another reason for the choice of hopper-like geometry for our upcoming experiment.

## Slide 5: Controlling Rheology via Boundary Conditions in Dense Granular Flows; Karen Daniels, et al.
Question: There was a brief mention of collaboration with Karen Hapgood (3-d printed coffee beans?) but no details were provided.
Answer: Yes, there is an ongoing collaboration with Karen Hapgood, in which we are working together to interpret the (complicated) photoelastic signals she and her group obtain from 3D printed photoelastic grains. The conclusion so far: this can be done, but there are some pitfalls that Farnaz and I have been working to help them understand. It may be necessary for them to go back into the lab to finalize some pieces. As for why I didn't give more details: since the lead authors on the study are from Karen Hapgood's team, I figured she would report on this rather than us. I'm not sure whether this is IFPRI-funded on her end, however?

## Slide 6: Controlling Rheology via Boundary Conditions in Dense Granular Flows; Karen Daniels, et al.
Question: What is working well?
Answer: The main apparatus runs just fine in its old configuration, and short lab trips suffice to go in to start/stop runs that are similar to existing data
  Caveat: changing to different wall to switch roughness is more time-consuming and needs to be more carefully planned with the rules (below)
Answer: We have received permission to conduct duration-limited and occupancy-limited research in our lab rooms, wearing masks, as long as lab safety hazards aren’t a problem (they aren’t)
Answer: Since the main apparatus is in its own small room, occupancy = 1, but it’s ours to allocate.
Answer: Current plan: go in ~ once a week, collect a new run, analyze it, repeat

## Slide 7: Controlling Rheology via Boundary Conditions in Dense Granular Flows; Karen Daniels, et al.
Question: What are Potential Roadblocks?
Answer: Data collection and analysis and discussion are not quite proceeding at a normal rate, including because turn-around time on glitches is lengthened
Answer: The main apparatus in its old configuration does not have good enough lighting to collect high-quality data: we will need to upgrade the lighting to provide separate red (unpolarized) and green (polarized) channels.
  The red/green LED order has now been placed, and building the new lighting setup should be possible within the constraints above.
  We’re uncertain how to implement the polarization until we try a few things in the lab.
  Hopefully, we don’t need to use the machine shop to complete construction (not currently operating).
Answer: The number of COVID-19 cases in NC is currently heading back towards ICU crisis levels, so it remains possible the our access to the lab will once again be curtailed. Getting some data onto disk now is our best protection against that possibility.